## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | As a student, I want to register and log in so that I can access the online examination system. | Must Have | Database | Vishva Dharshini | 3- Completed
1 | 1 | US02 | As a student, I want to start and manage my examination session so that I can attend the exam through the platform. | Must Have | US01 | Vishva Dharshini | 3- Completed
2 | 2 | US03 | As an invigilator, I want the system to monitor face presence so that face-missing and multiple-face events can be recorded. | Must Have | Camera, OpenCV | Vishva Dharshini | 3- Completed
2 | 2 | US04 | As an invigilator, I want browser activities to be recorded so that selected suspicious browser events can be reviewed. | Must Have | Examination Session | Vishva Dharshini | 3- Completed
3 | 3 | US05 | As an invigilator, I want an integrity score to be calculated from recorded browser events so that examination sessions can be analysed consistently. | Must Have | US04 | Vishva Dharshini | 3- Completed
3 | 3 | US06 | As an invigilator, I want to view and manage incidents with supporting evidence so that recorded events can be reviewed. | Must Have | US03, US04 | Vishva Dharshini | 3- Completed
4 | 4 | US07 | As an invigilator, I want examination sessions to be grouped using K-Means clustering so that session patterns can be analysed. | Should Have | US05, Pandas, Scikit-learn | Vishva Dharshini | 3- Completed
4 | 4 | US08 | As an invigilator, I want an AI-assisted report to be generated from session information so that examination results can be reviewed in a readable format. | Should Have | US05, LangChain | Vishva Dharshini | 3- Completed
5 | 5 | US09 | As an invigilator, I want a dashboard to view monitoring, analytics, incidents, and reports so that examination information is available in one place. | Must Have | US06, US07, US08 | Vishva Dharshini | 3- Completed
5 | 5 | US10 | As an invigilator, I want to export relevant examination data in JSON/CSV format so that records can be stored and reviewed outside the application. | Could Have | US05, US07, US08 | Vishva Dharshini | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7