## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vishva Dharshini | 2026-07-30 | Face monitoring was not recording the face-missing event correctly when the face moved out of the camera frame. | 2 | Vishva Dharshini | Logical | Updated the face monitoring logic and tested the event recording again. | 2026-08-01 | Closed | Face-missing event was recorded correctly after the fix.
2 | Vishva Dharshini | 2026-07-30 | Multiple-face events were not being recorded properly during camera monitoring. | 2 | Vishva Dharshini | Logical | Corrected the multiple-face detection and event logging logic. | 2026-08-02 | Closed | Multiple-face events were recorded successfully.
3 | Vishva Dharshini | 2026-08-07 | Browser tab switching was not updating the integrity score correctly. | 3 | Vishva Dharshini | Logical | Corrected the browser event penalty calculation and score update. | 2026-08-08 | Closed | Tab-switching penalty was applied correctly.
4 | Vishva Dharshini | 2026-08-10 | Incident evidence was not displayed correctly in the incident management section. | 4 | Vishva Dharshini | User Interface | Corrected the evidence display handling and tested the incident page again. | 2026-08-11 | Closed | Evidence was displayed correctly after the fix.
5 | Vishva Dharshini | 2026-08-15 | The examination dashboard required improvement in displaying session information clearly. | 5 | Vishva Dharshini | User Interface | Adjusted the dashboard presentation and verified the displayed information. | 2026-08-15 | Closed | Dashboard information was displayed more clearly.
6 | Vishva Dharshini | 2026-08-20 | Incomplete session data caused issues during K-Means analysis. | 5 | Vishva Dharshini | Logical | Added validation for the required data before performing clustering. | 2026-08-22 | Closed | Clustering worked correctly with valid session data.
7 | Vishva Dharshini | 2026-08-23 | AI report access was not properly validated for the selected examination session. | 5 | Vishva Dharshini | Logical | Added session ownership validation before generating the report. | 2026-08-24 | Closed | Report access was validated successfully.
8 | Vishva Dharshini | 2026-08-26 | Some parts of the project code required better organization for easier maintenance. | 4 | Vishva Dharshini | Maintainability | Reorganized the related logic into appropriate modules. | 2026-08-28 | Closed | Code structure was improved for easier maintenance.
9 | Vishva Dharshini | 2026-09-02 | Exported examination data required consistent formatting for further use. | 5 | Vishva Dharshini | Standards | Updated the export handling to maintain a consistent data format. | 2026-09-04 | Closed | Exported data followed the expected format.
10 | Vishva Dharshini | 2026-09-08 | The examination session information was not displayed consistently after session actions. | 3 | Vishva Dharshini | User Interface | Updated the relevant page handling and checked the session information again. | 2026-09-11 | Closed | Session information was displayed correctly.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others